## Slide 1
BCBS-MA Container Services Project Report as of 07/21/21
Executive Summary / Accomplishments / Upcoming Plans
Period 07/15 – 07/21
837 go-live delayed till July 25?? Performance testing and negative tests are in process. Volume related issue discovered during Tuesday July 13 testing that not all items are being generated for about a third of the claims. BCBS-MA team investigating.
835 results of big file run on legacy prod and OCP show Openshift runtime slower. For next OCP run, number of pods to be increased. Has this run complete? Results? Any parallel processing / concurrent thread processing concerns remaining?
Upgrade of dev to Service Mesh version 2.0.3 did not resolve TS005218429. Awaiting new must gather from Venkat per request on June 8. Case will be closed on July 28.
TS005701431 Drools jars not working with Springboot and Liberty. Support concludes application issue and thus out of scope from support perspective; however, a Springboot programmer did agree to review the code but no ETA on possible findings.
TS005802137 ACE to FTP server using certificates. Support has provided new instructions and requests that Venkat try them.
TS005792064 MQ Connect Reconnect. Per Sreenu ACE able to reconnect after MQ outage but Open Liberty on OCP was not. Support recommends opening new ticket for the Open Liberty issue.
TS005979854 Application pods not starting in staging with a worker node in uncordoned state. Cluster made operational by changing the storage to random pvc. Recommend closing this ticket. EDI team to have more discussion with infrastructure team to understand plan for prod env.
SOW end date extension completed. New end date is 9/24/21
Upcoming Plans
Review performance data. Produce deliverable after IBM / BCBS-MA joint review of test results. Need material from Venkat and / or Kevin.
Understand blockers for 837 production and assess go-live readiness.
Joint BCBS-MA and IBM project review sessions (July 22, 23, 26?)
Key Dates | Target Date | Status
Activity 7: Tuning Recommendations – need 835 perf testing redone, 837 perf testing completed, and negative scenarios completed to finalize this deliverable. | 2/28/ 2021 | Milestone Released
Activity 8 (month 1): Final Support Document – 12/2: Milestone released end of November | 10/30/20 | Complete
Activity 8 (month 2): Final Support Document Revised – 12/2: Milestone released end of November | 11/30/20 | Complete
Activity 8 (month 3): Final Support Document Revised | 12/31/20 | Complete
Activity 8 (month 4): Final Support Document Revised | 09/24/21 | 
Top Risk(s) or Issue(s) – See next page for Low Impact Items | Impact | Owner | Status
Issue: TS005701431 (sev 3): Drools jars not working with Springboot and Liberty Impact: All env. Opened per recommendation of Yi. Next Steps: Support concludes application issue which is out of scope for support; however, a Springboot programmer did agree to review the code but no ETA for any findings. | Medium | IBM Support | Open 05/20
Issue: TS005792064 (sev 3) MQ/JMS nodes do not reconnect after MQ outage. Impact: Have to restart all ACE / Websphere Liberty pods. Next Steps: During recent outage, ACE did reconnect to MQ. Support recommends separate case for Open Liberty not reconnecting. | Medium | IBM Support | Open, 6/01
Issue: TS006028998 (sev 2) IBM Licensing service is not reporting the license usage data for ACE containers running in OCP 4.6.12 . Impact: Unable to provide license usage for audits, etc. Next Steps: Able to now get license usage. Need to move to operator release of ACE to take advantage of full functionality of license advisor (Day 2 activity). Close this ticket? | Medium | IBM Support | Open, 6/28
Issue: TS005979854 (sev 2) Application pods are not starting up in staging. One worker node going into uncordoned state. Impact: OCP Stage environment is completely down and not usable. This is blocking any further delivery activities on 837 Transaction. Next Steps: Cluster operational by moving to random pvc storage. Close this ticket? | Showstopper. | IBM Support | Open, 6/23 Close???
Overall Status: Yellow 820 successfully live on May 9. 837 go live now July 25?? 835 redeployed on June 13. Performance testing and negative scenario testing needs to be completed. IBM Garage engagement ends when 820, 835, and 837 are all migrated to production, i.e. on July 25. New PCR end date extension completed.
Overall | Scope | Schedule | Resources | Budget
Key Final Outcome(s) | Target Date | Status
Phase 1 Release 1 Deploy to Prod 820 | May 9 | Complete
Phase 1 Release 1 Redeploy 835. | June 13 | Complete
Phase 1 Release 1 Deploy to Prod 837. | July 25?? | 

## Slide 2
BCBS-MA Container Services Project Report
Open Top Risk(s) or Issue(s) - Low Impact only | Impact | Owner | Status
Issue: TS005218429 (sev 2): issue with duplicate route created when IOR is enabled in OpenShift Service Mesh Impact: Not a showstopper, checking if any impact to prod. Next Steps: Upgrade did not resolve issue in Dev. June 8: Support requests new must gather from Venkat. Support will close case on July 28 if no further updates. | Low | IBM Support | Open, 03/15
Issue: TS005802137 (sev 3) Directions on how to configure App Connect Enterprise (ACE) to use ssh key authentication for connecting to FTP Server. Impact: Nice to have. Next Steps: New directions provided. Venkat needs to test. | Low | IBM Support | Open, 6/02
Overall | Scope | Schedule | Resources | Budget

## Slide 3
BCBS-MA Container Services Project Report
Closed Top Risk(s) or Issue(s) | Impact | Owner | Status
Issue: TS004623510 (sev 2, opened 12/4) a pod getting assigned to one of the nodes fails to start but when pod generated from same script/helm chart assigned to another node starts successfully. Impact: May further delay start of load / stress testing Resolution: Specify the ImagePullPolicy = Always on the helm install command | Medium | IBM Support | Closed, 12/16/20
Issue: TS004736029 (sev 1, opened 12/28) Dev and UAT openshift pods stuck in ImagePullBackOff status Impact: BCBS-MA QA team is blocked in DEV/UAT env as unable to deploy new code or code changes Resolution: OCS operator removed. Updated SCCs in the rook-ceph namespace to the original SCC. | High | IBM Support | Closed, 1/08/21
Issue: TS004821575 (sev 3, opened 1/14/21) CP4I 2020.1 upgrade. Needed clarity on if any account with cluster admin rights can upgrade. Impact: Upgrade delayed in Dev/UAT until answer provided Resolution: Support confirmed that yes it could be any account. Goutham confirmed understanding | Medium | IBM Support | Closed, 1/14/21
Issue: RHEL 02822376 NFSv4 NFSv4 Mount does not come up correct User/Group Impact: Transactions deployed in staging but unable to do testing Resolution: Isilon sets the group owner on files shared between ACE and external systems to “aceuser”. | High | IBM / RHEL Support | Unclear if ticket closed but issue is resolved.
Issue: Proactive ticket TS004863107 for the staging upgrade Ticket included an issue related to not being able to access some of the OCP clusters. Issue was resolved with a reboot. Unable to determine root cause as cluster log forwarding needs to be setup. Resolution: Closed ticket since no root cause can be found. If issue occurs after cluster log forwarding implemented then will open a new case |  | IBM Support | Closed, Feb 3
Issue: Proactive ticket TS004949008 for the dev/uat upgrade Resolution: Closed ticket. Remaining issue related to some common services not running has been opened on a new ticket. |  | IBM Support | Closed, Feb 22
Issue: Need performance test to start and IBM provided data needed for tuning recommendations including capacity Impact: BCBS environment may not be sized correctly for prod workload Next steps: Testing started!!! Need to provide Owen information from the testing so he can generate the deliverable. | High | BCBS-MA | Closed, Feb 23
Issue: TS004815266 (sev 2) umask configuration for pods (related to Liberty container but there are two parts to this ticket) Impact: Unclear. Needs to be 0006 and 0007 in stage and production. Next Steps: Closed ticket. |  |  | Closed, Mar 8
Overall | Scope | Schedule | Resources | Budget

## Slide 4
BCBS-MA Container Services Project Report
Closed Top Risk(s) or Issue(s) | Impact | Owner | Status
Issue: TS005070314 (sev 1): issue with common-services upgrade from 3.5.6 to 3.6.3 We updated the catalogsource for opencloud-operators in openshift-marketplace for ibm-common-service-catalog to latest . Impact: Unable to deploy to ace Next Steps: Bug found that will be fixed in the next Common Services 3.6 fixpack and in Common Services 3.7. Solution working and confirmed by BCBS-MA dev team. Support responding to questions on keeping custom certs working with fixpaks or new versions. | High | IBM Support | Closed, 03/17/21
Issue: TS005283642 (sev 2): issue with deploying new certificates with the wrong information. Certs are re-issued. need to remove old ones and put the new ones in place. Production Env. Impact: This is a showstopper Next Steps: Ticket closed Apr 5. | Medium | IBM Support | Closed, Apr 5
Issue: TS005396292 (sev 1): Unable to access Openshift 4.6.12 Cluster running on VMWare using OCP Console or OC command line. No changes were done to the cluster prior to the issue Impact: Unable to access the cluster. Next Steps: Installation of DataDog on the cluster appears to have broken the scc. Updating the scc resolved the issue. |  |  | Opened, Apr 9 Closed Apr 13
Issue: TS005316553 (sev 3): Istio Service Mesh - Enabling Automatic Route Creation – ior_enabled flag is not being saved with correct value Impact: Dev env. Opened per recommendation of Yi. Next Steps: Support has engaged Red Hat. Instructions on how to resolve provided to Venkat. Awaiting update from Venkat. | Low | IBM Support | Open,03/29 Closed, May 19
Issue: TS005551339 Sev 3 ACE bar override command not working. IBM support needs more info, awaiting feedback from BCBS-MA team. Impact: All env. Opened per recommendation of Yi. Next Steps: Support requesting more info. | Medium | IBM Support | Open,05/20 Closed, May 27
Issue: TS005585650 (sev 1): Users cannot login to Cloud Pak console using cloudctl in command line. Impact: Prod env. Next Steps: Recommended setting working in staging. | Medium | IBM Support | Open, 05/05 Closed, June 16
Issue: TS004870892 (sev 3): ACE container logs date/time stamp is in GMT. Logs written by IBM Production and application logs are in EST. In Docker file, we are defining environment ENV TZ=EST5EDT. This seems to work for Application logs and not for IBM Product logs. Impact: Not a showstopper. Want all logs in ET. Next Steps: Support provided more clarification on June 2. Awaiting feedback from Venkat. Support closed due to inactivity | Low | IBM Support | Open, 1/27 Closed, 6/30
Overall | Scope | Schedule | Resources | Budget